TEAM 1 MVP DOC

Hospital 30-Day Readmission Risk Prediction Platform

# 1. Purpose of This Document

This document defines the Minimum Viable Product (MVP) for the project across its three delivery sprints. For each sprint, it specifies the smallest functional slice that (a) delivers real, demonstrable value and (b) stays within the agreed project scope which is a full-stack hospital readmission risk platform built with HTML/CSS/JavaScript, FastAPI, Supabase , and a scikit-learn ML model trained on the provided 30K-row patient dataset.

The MVP for each sprint is progressively added onto the previous sprint’s MVPs, such that the entire MVP is a culmination of each of the sprint’s MVPs

# 2. Product Vision

Core value proposition: Enter or import patient discharge data → Get an instant, Model-backed risk score → act on it (registry, reporting, audit) with all of it behind a secure login.

# 3. Overall MVP Scope

| In Scope | Out of Scope (for this MVP) |
| --- | --- |
| Email/password auth (JWT sessions) | SSO / OAuth / MFA |
| Patient registry: view, search, add, bulk CSV import | Full patient record edit/deletion history & versioning |
| Single-patient risk prediction (RandomForest model) | Real-time streaming predictions / model retraining pipeline |
| Dashboard: key stats, charts, feature importance | Predictive analytics beyond 30-day readmission |
| CSV export of patients & predictions | PDF report generation, scheduled/emailed reports |
| Audit log of key actions | Fine-grained role-based access control (RBAC) enforcement UI |
| Supabase-ready backend with local SQLite fallback | Live production Supabase project management |
| Docker-based deployment | CI/CD pipeline, autoscaling, multi-region deployment |

# 4. MVP for each Sprint

## Sprint 1 — Project Planning & Setup

Sprint Goal: Establish the foundation for the project and its requirements, architecture, and a working environment, such that the Sprint 2 can build without rework

### Sprint 1 MVP Definition

The MVP for Sprint 1 is not a user-facing feature — it is a validated foundation. It is "complete" when a new developer can clone the repo, follow the setup steps, and run an empty-but-functional skeleton app end to end.

### MVP Deliverables

| # | Deliverable | Description | Acceptance Criteria |
| --- | --- | --- | --- |
| 1.1 | Requirements document | Finalized feature list, user roles (clinician, care coordinator, admin), and success criteria | Sign-off from team on scope table (Section 3) |
| 1.2 | System architecture diagram | Frontend (HTML/CSS/JS) → FastAPI → Services layer → Supabase/SQLite fallback → ML module | Diagram covers all 5 layers and data flow for one request (e.g., login) |
| 1.3 | Repository scaffold | Full folder structure created (app/, supabase/, templates/, static/, tests/, Docs/, etc.) | tree output matches signed-off structure; all __init__.py present |
| 1.4 | Environment configuration | .env / .env.example, config.py (Pydantic Settings), requirements.txt, .gitignore | App boots locally with uvicorn app.main:app --reload with no missing-module errors |
| 1.5 | Dataset validated | hospital_readmissions_30k.csv reviewed for schema, nulls, and value ranges | Data profiling confirms 30,000 rows, 11 usable features, no missing required columns |
| 1.6 | Supabase design decision | Schema for users, patients, predictions, audit_logs; local-fallback strategy documented | supabase/policies.md and fallback schema reviewed and approved |
| 1.7 | "Hello World" health check | A single working endpoint (/api/health) and one rendered page (/login) | GET /api/health returns 200; /login renders without errors |

### Sprint 1 Definition of Done

- Architecture and requirements documents approved by the team

- Repo scaffold pushed with correct structure

- App starts locally and via with zero errors, even with no real Supabase project configured

- Dataset validated and stored under Docs/

## Sprint 2 — Core Application Development

Sprint Goal: Deliver a functionally complete, single-user-tested application: the frontend pages, backend APIs, database layer, and trained ML model all working together.

### Sprint 2 MVP Definition

The MVP for Sprint 2 is: a logged-in clinician can add or import patients, request a risk prediction for a patient, and see it reflected on the dashboard — the shortest end-to-end path that proves every core layer works together.

### MVP Deliverables

| # | Deliverable | Description | Acceptance Criteria |
| --- | --- | --- | --- |
| 2.1 | Authentication | Signup/login endpoints, JWT issuance, /api/auth/me, Supabase-or-local-fallback logic | New user can sign up, log in, and reach /dashboard; invalid credentials rejected with 401 |
| 2.2 | Patient registry (backend + UI) | CRUD for individual patients, paginated list with search, CSV bulk import | Adding one patient and importing the 30k-row CSV both succeed; registry reflects both |
| 2.3 | ML model training pipeline | train_model.py cleans data, engineers features, trains RandomForest, saves model.pkl/scaler.pkl | Script runs standalone and produces a usable model with a reported AUC/classification report |
| 2.4 | Prediction API + UI | /api/prediction/predict scores a single patient; prediction page form + risk gauge | Submitting valid patient data returns a risk score, a Low/Medium/High label, and renders on the gauge |
| 2.5 | Dashboard | Aggregate stats, charts (destination mix, gender), feature importance, recent predictions | Dashboard loads without errors for a fresh account and updates after adding data |
| 2.6 | Reports (baseline) | /api/reports/summary, CSV export of patients and predictions | Summary numbers match underlying data; exported CSVs open correctly with expected columns |
| 2.7 | Audit logging (baseline) | Every login, signup, patient-add, CSV import, and prediction writes an audit record | Audit table/API shows entries corresponding to actions just performed |
| 2.8 | UI/UX baseline | Sidebar navigation, consistent design system across all 6 pages | All pages reachable, styled consistently, functional without console errors |

### Sprint 2 Definition of Done

- A user can complete the full loop: sign up → import/add patients → run a prediction → see it on the dashboard → export a report

- Model is trained on the real 30k dataset and loads successfully at runtime

- All API endpoints require authentication except signup/login

- No blocking bugs in the core happy path

## Sprint 3 — Testing & Deployment

Sprint Goal: Validate correctness and stability, package the application for deployment, and prepare it for a live demo.

### Sprint 3 MVP Definition

The MVP for Sprint 3 is: the application passes automated tests, runs reliably from a single Docker command, and can be demonstrated live without manual workarounds.

### MVP Deliverables

| # | Deliverable | Description | Acceptance Criteria |
| --- | --- | --- | --- |
| 3.1 | Automated test suite | Unit/integration tests for auth, patients, prediction, and reports (tests/) | All tests pass (pytest tests/ -v); auth, CRUD, prediction, and export flows each covered |
| 3.2 | Bug triage & fixes | Fix issues surfaced by testing (validation gaps, CSV import edge cases, malformed BP strings) | No known blocking or high-severity bugs remain open on core flows |
| 3.3 | Input validation hardening | Server-side validation for patient fields (gender, Yes/No, blood pressure format, destination) | Invalid payloads return 400 with a clear error message, verified by tests |
| 3.4 | Containerized deployment | Dockerfile builds and runs the app; documented deployment steps | docker build + docker run serves the app on the expected port with no errors |
| 3.5 | Environment/config finalization | Production-ready .env guidance (secret key rotation, CORS origins, optional Supabase connection) | README documents exactly which values must change before going live |
| 3.6 | Demo readiness | Seed/demo data path, walkthrough script, README covering setup + usage | A new team member can follow the README and run a full demo without assistance |
| 3.7 | Final documentation | Updated README, architecture notes, known limitations (e.g., synthetic-dataset model accuracy) | Reviewer can understand scope, setup, and limitations from documentation alone |

### Sprint 3 Definition of Done

- pytest tests/ passes with zero failures

- App deploys via Docker and is reachable end-to-end

- Demo walkthrough executed successfully at least once, start to finish

- Documentation reviewed and finalized for handoff/submission

# 5. Cross-Sprint Traceability

| Capability | Sprint 1 | Sprint 2 | Sprint 3 |
| --- | --- | --- | --- |
| Auth | Schema designed | Implemented & working | Tested, hardened, validated |
| Patient registry | Structure planned | CRUD + CSV import built | Validated, edge cases fixed |
| ML prediction | Dataset validated | Model trained + API built | Verified via tests, demoed |
| Dashboard / Reports | Wireframe / plan | Built with live data | Confirmed accurate, exported |
| Audit trail | Schema designed | Logging implemented | Verified complete & accurate |
| Deployment | Local env only | Local + Docker skeleton | Full Docker deployment, documented |

# 7. Success Criteria for the Overall MVP

The project MVP is considered successful when:

- A new user can sign up and log in without a pre-existing account.

- A patient can be added individually or via CSV import (validated against the 30k dataset).

- A risk prediction can be generated for a patient and is visibly reflected in the dashboard and reports.

- All core flows are covered by passing automated tests.

- The application can be built and run via Docker by someone outside the original dev team, using only the README.