SCRUM MASTER DOCUMENTATION

HOSPITAL READMISSION PREDICTION SYSTEM

Sprint Planning -

| Sprint | Goal | Duration | Deliverables | Status |
| --- | --- | --- | --- | --- |
| Sprint 1 | Requirement Analysis & Project Setup | Day 1-5 | Backlog, GitHub, Architecture | Completed |
| Sprint 2 | Core Application Development | Day 6-10 | Authentication, Patient Management, ML | Completed |
| Sprint 3 | Testing, Deployment & Delivery | Day 11-15 | Dashboard, Reports, Deployment | In Progress |

Product Backlog -

| ID | User Story | Priority | Status |
| --- | --- | --- | --- |
| PB-01 | Secure Login | High | Completed |
| PB-02 | Patient Management | High | Completed |
| PB-03 | Readmission Prediction | High | Completed |
| PB-04 | Dashboard | Medium | Completed |
| PB-05 | Reports | Medium | Completed |

Sprint Backlog -

| Task | Assigned To | Status |
| --- | --- | --- |
| Requirement Analysis | Business Owner | Done |
| Sprint Planning | Scrum Master | Done |
| GitHub Repository | Team Lead | Done |
| Dataset Analysis | ML Engineer | Done |
| Database Setup | Backend Team | Done |

Daily Scrum Log –

| Day | Date | Yesterday's Work | Today's Plan | Blockers | Status |
| --- | --- | --- | --- | --- | --- |
| Day 1 | 01-07-2026 | Identified project scope and objectives. | Conduct requirement analysis, perform sprint planning, create the product backlog, and assign initial tasks. | None | Done |
| Day 2 | 02-07-2026 | Requirement analysis completed. Sprint Planning conducted. Backlog created. GitHub repository initialized. | Start PostgreSQL setup, configure authentication, begin dataset preprocessing. | None | Done |
| Day 3 | 03-07-2026 | Completed database setup, configured SQL Alchemy, created the Users and Patients tables, and performed initial dataset cleaning and preprocessing.. | Attend Standup meeting. Develop Patient Management module Create CRUD APIs and deliverables. Start the machine learning workflow by conducting EDA. Create Git hub branches. | None | Done |
| Day 4 | 04-07-2026 | Attended Standup meeting and discussed the pending works and progress of the project. Developed patient Management module and done with the EDA. | Create database to store registered user details. Attend Standup meeting , discussion about encountered Blockers by the team. Analyze dataset characteristics . | YES | Done |
| Day 5 | 05-07-2026 | Attended Standup meeting and discussed the pending works and progress of the project. Coordinated with the team to find the appropriate solutions and solved the encountered Blockers. | Last day to complete sprint 1 tasks. Resolved Encountered Blocker by maintaining collaboration with team. Complete data preprocessing by performing feature scaling and splitting the dataset into training and testing sets. | None | Done |
| Day 6 | 06-07-2026 | Completed all the tasks of SPRINT1. Attended Standup meeting and discussed the pending works and progress of the project. Done with the data preprocessing by performing feature scaling and splitting the dataset into training and testing sets. | To begin the new phase SPRINT2 tasks. Create the database tables and push it in GitHub. Initiate the Model Training phase. Push Frontend files into GitHub. Implementation of API endpoints. | None | Done |
| Day 7 | 07-07-2026 | Attended Standup meeting and discussed the pending works and progress of the project. Created database tables and started with the model training. Implemented API endpoints. | Attend Standup meeting Push Product sprint ppt demo into git hub. Add and push audit.html, patients.html, and reports.html to the frontend branch.  Add and push patients.css and styling files with the required styling.  Create audit.js, patients.js, and reports.js, and add the corresponding JavaScript code files to git hub. | YES | Done |
| Day 8 | 08-07-2026 | Attended Standup meeting and discussed the pending works and progress of the project. Pushed all the project related code files into the project git hub repository. | Attend Standup meeting Resolved Encountered Blocker by maintaining collaboration with team. Prepare Product Demo And prepared TDD Demo. Research about additional features required for the project enhancement. | None | Done |
| Day 9 | 09-07-2026 | Attended Standup meeting and discussed the pending works and progress of the project. Researched the additional features required for the project enhancement. | Attend Standup meeting . Learnt about MVP and TDD topics. | None | Done |
| Day 10 | 10-07-2026 | Attended Standup meeting and discussed the pending works and progress of the project. Got an idea on MVP and TDD topics. | Last day to complete sprint 1 tasks. Prepare TDD and MVP files by the team and push into Git Hub. | None | Done |
| Day 11 | 11-07-2026 | Pushed all the important files into GitHub | To make the application work which we have created so that we can complete the next steps of improving the UI and adding the new feature. | None | Done |
| Day 12 | 12-07-2026 | The application task has done the improvement of UI discussed with the team. | Encountered some bugs. Application required files pushed into GitHub but still encountered bugs. | None | Done |
| Day 13 | 13-07-2026 | The backend team worked with the code related to applications in which bugs are encountered | Discussed the resolution for the encountered bugs and identified the approach to solve them. | None | Done |
| Day 14 | 14-07-2026 | All the bugs or blockers resolved. | Prepare final project Demo | None | Done |
| Day 15 | 15-07-2026 |  |  |  |  |

Project Progress Log -

| Day | Date | Activity | Completed By | Remarks |
| --- | --- | --- | --- | --- |
| Day 1 | 01-07-2026 | Started all the tasks related to SPRINT 1. Identify Project Scope. Business requirements discussed, project scope finalized, Sprint Planning completed, Product Backlog prepared, GitHub repository created, project architecture finalized. Product Owner uploaded the Product Requirements Document (PRD) and Team Lead/Developer uploaded the project planning and technical documentation to GitHub. | Business Owner, Scrum Master, Team Lead | Completed successfully |
| Day 2 | 02-07-2026 | PostgreSQL database setup started, Fast API project initialized, authentication module development started, dataset analysis and preprocessing initiated. | Backend, Database, ML Engineer | Completed successfully |
| Day 3 | 03-07-2026 | Attended Standup meeting discussed about blockers, Completed data preprocessing. Performed CRUD operations, APIs and Frontend for patient management . med EDA. | Backend ML Engineer Developer | Completed successfully |
| Day 4 | 04-06-2026 | Attended Standup meeting encountered the blockers co-ordinated with the team to find the appropriate solutions and solved the encountered Blockers. Analyzed dataset characteristics . Create database to store registered user details. | Backend ML Engineer Business Owner, Team Lead, | Encountered Blockers. |
| Day 5 | 05-07-2026 | Completed all the related tasks of SPRINT 1. Resolved Encountered Blocker by maintaining collaboration with team. Completed data preprocessing by performing feature scaling and splitting the dataset into training and testing sets. Gathered and analyzed the functional requirements for the project. | By Team | Resolved the Encountered Blockers successfully. |
| Day 6 | 06-07-2026 | Started with the SPRINT 2 tasks. Created the database tables and pushed it in GitHub. Initiated the Model Training phase. Pushed required Frontend files into the GitHub. | Backend ML Engineer Developer | Completed successfully |
| Day 7 | 07-07-2026 | Push Product sprint ppt demo into git hub. Add and push audit.html, patients.html, and reports.html to the frontend branch.  Add and push patients.css and styling files with the required styling.  Create audit.js, patients.js, and reports.js, and add the corresponding JavaScript code files to git hub. | Product Owner Backend | Encountered Blockers. |
| Day 8 | 08-07-2026 | Resolve Encountered Blocker by maintaining collaboration with team. Researched about additional features required for the project enhancement. | By Team | Resolved the Encountered Blockers successfully. |
| Day 9 | 09-07-2026 | Learn and Prepare a TDD file and also MVP file for the project. | By Team | Completed successfully |
| Day 10 | 10-07-2026 | Complete all the tasks related to SPRINT 2. Done with the TDD file and MVP file and uploaded into Git Hub. | By Team | Completed successfully |
| Day 11 | 11-07-2026 | To make the application work which we have created so that we can complete the next steps of improving the UI and adding the new feature | Backend | Completed successfully |
| Day 12 | 12-07-2026 | Cleared some bugs and pushed it into GitHub but still encountered bugs. | Backend(Database Manager and Developer) | Encountered Bugs |
| Day 13 | 13-07-2026 | Discussed the resolution for the encountered bugs and identified the approach to solve them. | Backend | Completed successfully |
| Day 14 | 14-07-2026 | Prepare final project Demo | Backend | Completed successfully |
| Day 15 | 15-07-2026 | Tested and deployed the project | Team | Completed successfully |

Blocker Tracking Log –

| Day | Date | Description | Owner | Status |
| --- | --- | --- | --- | --- |
| Day 4 | 04-07-2026 | Local PostgreSQL database was inaccessible to other team members. So Resolved by migrating to Supa base (cloud PostgreSQL) for shared database access. | Team Lead(Database Manager) | Done |
| Day 4 | 04-07-2026 | Encountered a file structure conflict. Resolved by adopting a compatible project folder structure. | Backend | Done |
| Day 7 | 07-07-2026 | Encountered limitations using Stream lit which did not meet the project’s backend API requirements. Resolved is made by switching to Fast API and the backend API development resumed . | Backend | Done |
| Day 8 | 08-07-2026 | Class imbalance affected ML predictions. Evaluated with ROC-AUC and planned data balancing. | ML Engineer | Done |
| Day 9 | 09-07-2026 | Encountered bugs with Authentication where Supa base did not detect logins so solved using HTTPX. | Developer and Database Manager | Done |
| Day 11 | 08-07-2026 | JS did not work properly So updated JS for adding patients. | Developer | Done |
| Day 12 | 12-07-2026 | Backend was not integrated with supa base so updated Supa base tables for better patient depiction. | Database Manager | Done |
| Day 14 | 14-07-2026 | Improper Data Visualization | Backend | Done |

Scrum Meeting Minutes –

| Day | Date | Attendees | Actions |
| --- | --- | --- | --- |
| Day 1 | 01-07-2026 | Team | Start with the SPRINT1 and Identify Project Scope and features. |
| Day 2 | 02-07-2026 | Team | Gather required information about the project. |
| Day 3 | 03-07-2026 | Team | About database authentication , Fast APIS initialization and dataset analysis and data processing. |
| Day 4 | 04-07-2026 | Team | Perform CRUD operations, APIs and Frontend for patient management and performed EDA. |
| Day 5 | 05-07-2026 | Team | Discussed the solution for encountered blocker and final SPRINT1 tasks. Perform feature scaling and splitting the dataset into training and testing sets. Gathered and analyzed the functional requirements for the project. |
| Day 6 | 06-07-2026 | Team | Start with the SPRINT 2 tasks. Create the database tables and push required Frontend files into in to GitHub. Initiate the Model Training. |
| Day 7 | 07-07-2026 | Team | Push Product sprint ppt demo into git hub. Add and push audit.html, patients.html, patients.css, styling files and reports.html to the frontend branch. Create audit.js, patients.js, and reports.js, and add the corresponding JavaScript code files to git hub. |
| Day 8 | 08-07-2026 | Team | Discussed the solution for encountered blocker. Research about additional features required for the project enhancement. |
| Day 9 | 09-07-2026 | Team | Learn and Prepare a TDD file and also MVP file for the project. |
| Day 10 | 10-07-2026 | Team | Discussed the final SPRINT2 tasks and solution for encountered blocker. Upload the TDD and MVP files into GitHub. |
| Day 11 | 11-07-2026 | Team | Test end to end the project application. |
| Day 12 | 12-07-2026 | Team | Discussed the encountered blockers . |
| Day 13 | 13-07-2026 | Team | Fixed the important blockers related to project applications. |
| Day 14 | 14-07-2026 | Team | Prepare final project Demo. |
| Day 15 | 15-07-2026 | Team | Discussed about testing and deployment process |